## Audit Overview
Field | Details
Audit Title | UX Audit – Registration & Login
App Name | eZhire
Auditor | [Your Name]
Date | [Insert Date]
Platform Tested | Android
App Version | [Insert Version]
Device | [Insert Device]
Language Tested | English

## Test Steps
Step No. | Action Performed | Expected Result | Actual Result | Pass/Fail | Comments
1 | Open app | Home screen loads | Home screen appears | ✅ | N/A
2 | Tap “Continue with Email” | Email input screen appears | Email screen shown | ✅ | -
3 | Enter invalid email | Should show validation error | No error shown | ❌ | Missing validation
4 | Press back | Return to welcome screen | Works as expected | ✅ | -
5 | Switch language to Arabic | UI switches | Works correctly | ✅ | Arabic button could be clearer

## Issues Log
Issue ID | Screen / Area | Description | Screenshot Attached | Severity | Recommendation | Status
UX-001 | Onboarding | Tagline is unreadable due to low contrast | Yes | Medium | Add overlay or increase font contrast | Open
UX-002 | Registration Icons | No label for social icons | Yes | Medium | Add “Continue with Google/Facebook” below icons | Open
UX-003 | Email Field | Placeholder says 'Enter mail' – unprofessional | Yes | Low | Use “Enter your email” | Open
UX-004 | Progress Indicator | 1/3 indicator has no context | Yes | Low | Add labels (e.g., Email > OTP > Profile) | Open
UX-005 | Country Code | Defaulted to Pakistan without prompt | Yes | Medium | Add searchable country picker | Open

## Follow-Up Actions
Action Item | Assigned To | Target Date | Status | Notes
File issues in Jira | UX Auditor | [Insert Date] | ⏳ In Progress | -
Review with design team | UX Lead | [Insert Date] | ⏳ Not Started | -
Retest after fix | QA Team | [Insert Date] | 🔜 Scheduled | -